## Overview
Medical Frailty Project Workplan
January 30, 2026 Prepared by Manatt Health
Background: Under H.R.1, states implementing Medicaid work reporting requirements must exempt individuals who are medically frail. The statute requires states to attempt to verify medical frailty exemptions ex parte—using data already available to the state, where possible, without requiring information from individuals. Ensuring that medically frail individuals are identified in an accurate and timely way is a core implementation requirement—not only to protect eligible individuals whom Congress intended to exempt but also to reduce administrative burden for states. With an effective date less than a year away, time is of the essence. States face compressed timelines to operationalize new work reporting requirements alongside other substantial systems, policy, and operational changes. Without a clear approach to implementing the medical frailty exemption, states risk relying on manual or paper-based verification processes, which would increase provider burden and create avoidable delays in exemptions for eligible individuals. To support states in meeting this compressed implementation timeline, and to accompany the Operationalizing the Medical Frailty Exemption: A Step by Step Implementation Toolkit for States (see Resources tab), the State Health and Value Strategies (SHVS) and Manatt teams developed this structured Medical Frailty Project Workplan, reflected in the accompanying "Sample Workplan" tab, that lays out a sequenced, implementation-ready approach for operationalizing the exemption. All dates included in the workplan are illustrative and intended to support planning—states may need to adjust sequencing and timelines based on policy decisions and operational readiness. The workplan is organized around key milestones, including: establishing cross-division governance and stakeholder engagement processes, to include meaningful involvement of individuals with lived experience; defining medical frailty in alignment with federal guidance and state policy goals; developing and validating diagnosis- and utilization-based code lists using claims and encounter data; testing approaches within Medicaid Management Information Systems; developing a medical frailty screener; and establishing business rules related to exemption duration, re-verification, and submitting documentation. Together, these milestones are designed to help states move quickly from policy interpretation to operational execution. States may customize and modify this tool as they see fit to best meet their needs. For additional information, see the "Resources" tab.

## Sample Workplan
Medical Frailty Project Workplan
Last Updated: January 30, 2026 |  |  | 2026 | [51 empty] | 2027
|  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  | Feburary |  |  |  | March |  |  |  |  | April |  |  |  | May
| Due Date | Status | 2025-01-05 | 2025-01-12 | 2025-01-19 | 2025-01-26 | 2025-02-02 | 2025-02-09 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 2025-03-30 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-04-27 | 2025-05-04 | 2025-05-11 | 2025-05-18 | 2025-05-25 | 2025-06-01 | 2025-06-08 | 2025-06-15 | 2025-06-22 | 2025-06-29 | 2025-07-06 | 2025-07-13 | 2025-07-20 | 2025-07-27 | 2025-08-03 | 2025-08-10 | 2025-08-17 | 2025-08-24 | 2025-08-31 | 2025-09-07 | 2025-09-14 | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2025-01-04 | 2025-01-11 | 2025-01-18 | 2025-01-25 | 2025-02-01 | 2025-02-08 | 2025-02-15 | 2025-02-22 | 2025-03-01 | 2025-03-08 | 2025-03-15 | 2025-03-22 | 2025-03-29 | 2025-04-05 | 2025-04-12 | 2025-04-19 | 2025-04-26 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31
Establish Cross-Division Governance Structure
Stand up cross-division governance structure for core work requirements team | 2026-01-01 | Complete | 2026-01-01
Engage agencies, and additional partners, to support implementation and define medical frailty | 2025-01-30 | In Progress |  | 2026-01-30
Identify individuals with lived experience and establish ongoing engagement mechanism (e.g., advisory group, focus groups, or listening sessions) to inform the definition, implementation, and ongoing refinement of medical frailty exemptions approach | 2025-01-30 | In Progress |  | 2026-01-30
Define Medical Frailty
Develop medical frailty definitions (see SHVS model definitions, included in Resources tab) | 2025-02-13 | In Progress | [5 empty] | 2026-02-13
Identify Medicaid Programs Where Eligibility Aligns with Medical Frailty Definitions
Conduct crosswalk of existing Medicaid programs and services to identify overlap with medical frailty exemptions (e.g., expansion adults who are enrolled in home and community based services waivers or specialy managed care programs) | 2026-03-02 | Not Started | [8 empty] | 2026-03-02
Develop and Validate a Code List for Data Verification
Identify diagnosis and utilization codes for claims data verification | 2026-03-13 | Not Started | [9 empty] | 2026-03-13
Compare diagnosis and utilization code list with peer state examples | 2026-03-27 | Not Started | [11 empty] | 2026-03-27
Finalize code list | 2026-04-03 | Not Started | [12 empty] | 2026-04-03
Conduct Medicaid Management Information System (MMIS) Data Analysis Testing
Conduct initial testing using historical MMIS data to assess how many individuals would have qualified for an exemption over the past three and six months | 2026-04-17 | Not Started | [14 empty] | 2026-04-17
Set thresholds for encounter frequency and lookback periods | 2026-04-30 | Not Started | [16 empty] | 2026-04-30
Validate the code list and methodology against historical MMIS data | 2026-04-30 | Not Started | [16 empty] | 2026-04-30
Develop business rules that establish duration limits for codes, where clinically appropriate | 2026-04-30 | Not Started | [16 empty] | 2026-04-30
Schedule monthly or quarterly updates to reflect new codes or evolving utilization patterns | Ongoing | Not Started
Leverage Supplemental Nutrition Assistance Program (SNAP) Work Requirements Exemptions
Identify criteria for SNAP work requirements exemptions and build data infrastructure for carrying exemptions over. | 2026-04-30 | Not Started | [16 empty] | 2026-04-30
Leverage Medicaid Managed Care Plan (MCP) Information
Analyze the typical lag between when a member receives a service and when State records it as an encounter | 2026-01-30 | Not Started |  |  |  | 2026-01-30
Engage with plans to understand ability to share near-real-time service utilization reports or encounter-level data (if encounter lag is too long) | 2026-02-13 | Not Started |  |  |  |  | 2026-02-13
Establish data-matching protocols to integrate case management information with MMIS or state eligibility systems | 2026-04-30 | Not Started | [16 empty] | 2026-04-30
(If needed) Implement contract updates to strengthen data reporting requirements | 2026-06-30 | Not Started | [25 empty] | 2026-06-30
Link to Health Data Utilities (HDUs), Health Information Entities (HIE), and All Payer Claims Database (APCD)
Conduct a comprehensive assessment of available data from State HDUs, HIEs, and APCD (where available) to support implementation | 2026-05-01 | Not Started | [16 empty] | 2026-05-01
Build connections to these data sources if determined useful (e.g., to ingest more real-time clinical data) and conduct testing | 2026-07-31 | Not Started | [29 empty] | 2026-07-31
Update Existing (or Develop New) Medically Complex Screener to Support Medical Frailty Exemptions
Update application and renewal forms required to include medically complex screener at application and renewal (including 6-month compliance reporting). (Applications and renewals forms should be available to be submitted via all modalities: in-person, by mail, and by telephone.) | 2026-05-29 | Not Started | [20 empty] | 2026-05-29
Conduct usability testing of the medically complex screener and related application and renewal forms with individuals with lived experience | 2026-05-29 | Not Started | [20 empty] | 2026-05-29
Develop Process for Individual-Submitted Documentation
Develop policy and operational process for allowing individuals to submit documentation to the state (e.g., provider form or medical records) demonstrating medical frailty | 2026-06-05 | Not Started | [21 empty] | 2026-06-05

## Resources
Medical Frailty Project Workplan Resources
Updated January 30, 2026
Resource | Link
Medicaid Work Reporting Requirements: Implementation Planning Milestones | Linked Here
Work Reporting Requirements: State Considerations When Defining Medical Frailty | Linked Here
Leveraging Managed Care Plans to Support Implementation of Medicaid Work Reporting Requirements | Linked Here
Operationalizing the Medical Frailty Exemption: A Step by Step Implementation Toolkit for States | Linked Here
Designing Effective Verification Pathways for Exempt Populations at Heightened Risk of Coverage Loss Under Mandatory Work Reporting Requirements | Linked Here
Support for this toolkit was provided by the Robert Wood Johnson Foundation. The views expressed here do not necessarily reflect the views of the Foundation.
ABOUT THE ROBERT WOOD JOHNSON FOUNDATION
The Robert Wood Johnson Foundation (RWJF) is a leading national philanthropy dedicated to taking bold leaps to transform health in our lifetime. Through funding, convening, advocacy, and evidence-building, we work side-by-side with communities, practitioners, and institutions to get to health equity faster and pave the way together to a future where health is no longer a privilege, but a right. RWJF believes that achieving strong, lasting connections across the healthcare, public health, and social services systems helps build healthier and more equitable communities that provide everyone a fair and just opportunity for health and wellbeing.
ABOUT STATE HEALTH AND VALUE STRATEGIES—PRINCETON UNIVERSITY SCHOOL OF PUBLIC AND INTERNATIONAL AFFAIRS
State Health and Value Strategies (SHVS) assists states in their efforts to transform health and healthcare by providing targeted technical assistance to state officials and agencies. The program is a grantee of the Robert Wood Johnson Foundation, led by staff at Princeton University’s School of Public and International Affairs. The program connects states with experts and peers to undertake healthcare transformation initiatives. By engaging state officials, the program provides lessons learned, highlights successful strategies, and brings together states with experts in the field. Learn more at www.shvs.org.
ABOUT MANATT HEALTH
This toolkit was prepared by Kinda Serafi and Linda Sears. Manatt Health, a division of Manatt, Phelps & Phillips, LLP, is an integrated legal and consulting practice with over 160 professionals in nine locations across the country. Manatt Health supports states, providers, and insurers with understanding and navigating the complex and rapidly evolving healthcare policy and regulatory landscape. Manatt Health brings deep subject matter expertise to its clients, helping them expand coverage, increase access, and create new ways of organizing, paying for, and delivering care. For more information, visit https://www.manatt.com/health.

## Look-Up (hidden)
Complete
In Progress
Not Started